Delivery Plan for the Long Term Strategy for Population Surveys in Scotland 2009 – 2019

1. The Scottish Government’s Long Term Strategy for Population Surveys in Scotland 2009 – 2019
 was originally published in June 2009 with a refresh published in March 2012. This paper sets out the delivery plan for the strategy.

2. Table 1 on the following page shows the main pieces of work that have been identified and the long-term aims that all work is progressing toward. Work completed in 2009 to 2012 is noted in grey and details have been removed.
3. There are four strands to the strategy:

· Core questions and pooled sample 
· Respondent burden and response rates 
· Analysis and dissemination

· Scottish Government cross-sectional surveys
Annex A, that begins on page 3, provides more detail on the pieces of work currently planned for action.  
4. This delivery plan will be updated biannually for the meetings of the Scottish Population Survey Co-ordinating Committee.

5. Work will be taken forward by the Scottish Population Survey Working Group and overseen by the Scottish Population Surveys Co-ordinating Committee. The remits and membership of the Committee and the Working Group can be seen on the Population Surveys webpage
.
Office of the Chief Statistician and Performance
Scottish Government 

DATE OF LAST UPDATE: FEBRUARY 2013 

	
	Harmonisation
	Data management


	Respondent rates and respondent burden


	Analysis and dissemination


	SHS,  SCJS and  SHeS

	Work complete

2009 – 2012
	Procurement Review

Progress core question harmonisation

Review core questions

Finalise wording of core questions
All core questions included in major SG surveys 


	Develop quick response system to identify field work activity

Investigate a centralised sampling system 

Instigate centralised sampling for the major SG surveys
	Investigate response rates 

Investigate ways to improve response rates
	Investigate the costs and benefits of clustering

Publish a user guide of topic/item coverage in surveys

Develop guidance for informed consent forms and permissions statements
	SHS Review

Review purpose and content of all major SG cross-sectional surveys in co-ordination with each other 

Procure major SG surveys in line with recommendations from the procurement review

First year of fieldwork for the centrally sampled surveys under new contracts

	
	Core questions and pooled sample
	Response rates and respondent burden
	Analysis and dissemination
	Scottish Government cross-sectional surveys

	2013
	Investigate the requirement for a method to impute missing data for core variables

Monitor the topic coverage of other surveys to assess opportunities for harmonisation and efficiencies

Promote centralised sampling knowledge and resources  to other surveys across Scotland 

Examine  the performance of core questions and review if necessary
	Continuous monitoring of respondent burden 

Monitoring of survey fieldwork outcomes 

Monitor developments in relation to alternative modes of data collection


	Review reporting thresholds

Develop dissemination strategy for pooled samples

Develop weighting procedures for the individual surveys and pooled sample

Consider options for dissemination of themed analysis

Provide weights for individual surveys and the pooled data

Analyse and disseminate pooled data
Work with AQMeN to disseminate survey data through events
	Investigate the standardisation of data storage practices for major SG surveys and pooled sample

Coordinate survey technical reports and user guides to facilitate understanding and effective use of survey data

	
	
	
	Review the dissemination and data access procedures of the surveys and consider the development of harmonised dissemination and data access

	2014 - 2015
	Investigate using harmonised data to create an expanded sampling frame


	Analysis of non-response by comparing survey and census non-response patterns 

Pilot alternative modes of data collection
	
	2015: Review purpose and content of surveys and re-procure contracts if continuing

	2016 - 2019
	Align local surveys with the co-ordination process


	Subsequent work depends on the results of investigations and reviews of emerging technologies and investigations
	
	


Annex: Detail of work to be taken forward over 2013
The details of the delivery tasks for 2013 have been divided into continuous activities and more distinct projects. The continuous activities are expected to require regular low level input (e.g. monitoring fieldwork outcomes) or a watching brief (e.g. monitoring developments in relation to alternative modes of data collection). While it would be beneficial to the delivery of the long-term strategy for the Scottish Government to be more pro-active in relation to some of these activities, due to limited resources we are restricted to being proactive and responding to opportunities that arise. 
The distinct projects are pieces of work which require more concentrated resources over a specific period of time. 
Time specified for tasks is approximate.

Ongoing Monitoring Activities

	Monitor the topic coverage of other surveys to assess opportunities for harmonisation and efficiencies

	Description
	Monitor the questions included in other surveys in Scotland. If opportunities arise, propose that SG core questions should be included and/or question wording should be modified to replicate SG core.  

	Output
	Capitalise on opportunities for harmonisation and efficiency savings. 

	Lead
	Office of the Chief Statistician and Performance

	Other groups involved
	Managers of other surveys

	Time needed
	Ongoing

	Start date
	Summer 2012

	Planned completion date
	Ongoing


	Promote centralised sampling knowledge and resources to other surveys across Scotland

	Description
	Through the development and delivery of the centralised sampling project the SG gained a detailed knowledge of survey sampling. This resource should be shared with other public bodies which deliver surveys in Scotland.  

	Output
	Assistance for other surveys.

(As a result of this strand, OCSP will be selecting the sample for the Scottish Social Attitudes Survey from 2013 onwards) 

	Lead
	Office of the Chief Statistician and Performance

	Other groups involved
	Managers of other surveys

	Time needed
	Ongoing

	Planned start date
	Summer 2012

	Planned completion date
	Ongoing


	Continual Monitoring of Respondent Burden

	Description
	Monitor the number and length of Scottish Government population surveys in the field. Data linkage should be considered as an option for meeting new and changing requirements associated with our surveys. The new Data Sharing and Linking Service will provide a resource to enable new linkages to take place from Dec 2013.

	Output
	Report to SPSCC as necessary

	Lead
	Survey Harmonisation Co-ordinator

	Other groups involved
	Survey Managers

Contractors

	Time needed
	Ongoing

	Planned start date
	Ongoing

	Planned completion date
	Ongoing


	Monitoring of survey fieldwork outcomes

	Description
	For the 3 surveys each of the contractors will supply the SG with quarterly fieldwork outcome reports. These reports will be analysed to ensure that the outcomes meet the levels specified in the survey contracts. 

	Output
	Sign-off on quarterly fieldwork, any issues raised with survey managers and contractors. 

	Lead
	Survey Harmonisation Co-ordinator

	Other groups involved
	Survey Managers

Contractors

	Time needed
	Ongoing

	Planned start date
	May 2012 

	Planned completion date
	Ongoing


	Monitor developments in relation to alternative modes of data collection

	Description
	Monitor research and changes made in relation to modes of data collection in other surveys in Scotland, UK or elsewhere.  (A comprehensive study was completed by ONS in 2010 – available here)

	Output
	Updates for SPSCC when required

	Lead
	Survey Harmonisation Co-ordinator

	Other groups involved
	Survey Managers

	Time needed
	Ongoing

	Planned start date
	Ongoing

	Planned completion date
	Ongoing


Distinct Projects
	Investigate the requirement for a method to impute missing data for core variables

	Description
	Imputing can be used to address unit (an eligible sample unit fails to participate in the survey) and item (some questions are not answered by a responding unit) non-response. This investigation will be concerned with item non-response as unit non-response is addressed by weighting. The investigation will review existing survey practices for imputation and assess the requirements for applying imputation to data from the 2012 survey sweeps. 

	Output
	Short paper examining current practices and appraisal of future options. 

	Lead
	Office of the Chief Statistician and Performance

	Other groups involved
	Survey Managers

	Time needed
	4 weeks

	Planned start date
	Summer 2012

	Planned completion date
	On hold


	Examine the performance of core questions and review if necessary

	Description
	An important element of the development of the pooled sample will be the quality assurance of pooled data. The QA process will incorporate an assessment of the performance of the core questions across all three surveys

	Output
	Recommendations on the future of core questions

	Lead
	Office of the Chief Statistician and Performance

	Other groups involved
	Topic lead analysts

	Time needed
	2 months 

	Planned start date
	August 2013

	Planned completion date
	October 2013


	Review Reporting Thresholds 

	Description
	Investigate procedures in place to avoid reporting on small numbers which may be disclosure or unreliable and look at areas for improvement. Make recommendations and produce guidance.  

	Output
	Paper and recommendations, including minimum sample cell requirements for publication.

	Lead
	Office of the Chief Statistician and Performance

	Other groups involved
	Survey Managers

	Time needed
	4 weeks

	Planned start date
	On hold

	Planned completion date
	


	Develop dissemination strategy for pooled samples

	Description
	In developing the strategy the following issues need to be considered:

· Needs and expectations of users of the data
· Guidance for users on most appropriate sources of data (Pooled sample/ individual surveys/ IHS) 

· Consider previous work on links with IHS and other surveys

	Output
	Dissemination Strategy for Pooled Sample (Report)

	Lead
	Survey Harmonisation Co-ordinator

	Other groups involved
	Survey Managers

	Time needed
	3 months

	Planned start date
	September 2012

	Planned completion date
	January 2013


	Develop weighting procedures for the individual surveys and pooled sample

	Description
	From 2012 onwards the weighting of survey data will be undertaken by the SG rather than the survey contractors. The procedures for deriving the weights need to be in place prior to receipt of the survey data in 2013.  

	Output
	Full weighting methodology and code which can be implemented upon receipt of survey data. 

	Lead
	Survey Harmonisation Co-ordinator

	Other groups involved
	Methodology Advisory Service

	Time needed
	8 months

	Planned start date
	January 2012

	Planned completion date
	March 2013


	Dissemination of themed analysis/topic reports

	Description
	Investigate ways to increase the dissemination of Scottish Government analysis and other analysis of survey data.  Investigate the production of themed reports using Scottish Government survey data.

	Output
	Increase use of Scottish Government survey data across stakeholders and researchers

	Lead
	Communities Analytical Services Division

	Other groups involved
	SHS Lead Analysts Network
AQMeN

	Time needed
	Ongoing

	Planned start date
	Ongoing

	Planned completion date
	Ongoing


	Work with AQMeN to disseminate survey data through events

	Description
	AQMeN have funding available to run a number of training events and workshops to promote the use of Scottish and UK Datasets. AQMeN could work with the SG to deliver events to coincide with the release of new survey findings and data. 

	Output
	Events/workshops promoting the use of survey data and survey findings

	Lead
	AQMeN

	Other groups involved
	Survey managers 

Office of the Chief Statistician and Performance

	Time needed
	TBC

	Planned start date
	Summer 2013

	Planned completion date
	End of 2013


	Provide weights for individual surveys and pooled data

	Description
	The derivation of the survey weights was previously undertaken by survey contractors. This will be completed by OCSP for survey data from 2012 onwards.

	Output
	Range of required weights (e.g. household, individual, etc) for individual surveys and the pooled sample

	Lead
	Office of the Chief Statistician and Performance

	Other groups involved
	Survey managers and nominated analysts for QA

	Time needed
	Dates for individual surveys to be confirmed

	Planned start date
	May 2013

	Planned completion date
	August 2013


	Analyse and disseminate pooled data

	Description
	The work will include: weighting the pooled sample; dataset quality assurance; analysis and preparation of outputs; and quality assurance of outputs. Details of the proposals are specified in the dissemination plan for pooled samples.

	Output
	Dataset and dissemination of findings

	Lead
	Office of the Chief Statistician and Performance

	Other groups involved
	Nominated analysts for QA

	Time needed
	5 months

	Planned start date
	July 2013

	Planned completion date
	November 2013


	Investigate the standardisation of data storage practices for major SG surveys and pooled sample

	Description
	Data storage and data conversion (SPSS to SAS and SAS to SPSS) is being considered for SHS data. Wider work will include consideration of storing data in XML format or some other platform-independent format.

	Output
	Recommendations for the storage of SHS data which are applicable for data from the other surveys and the pooled sample

	Lead
	SHS Survey Manager

	Other groups involved
	Survey Managers

	Time needed
	4 months

	Planned start date
	November 2012 (though preparatory work from summer 2012)

	Planned completion date
	March 2013


	Share best practice and consider potential for harmonised approach to microdata release

	Description
	For each of the surveys there are procedures for allowing researchers access to detailed (potentially disclosive) data where a strong argument can be made. Consider improvements and sharing of processes across surveys. 

	Output
	Recommendations for harmonised procedures

	Lead
	Office for the Chief Statistician and Performance

	Other groups involved
	Survey Managers

	Time needed
	TBC

	Planned start date
	July 2012

	Planned completion date
	June 2013


	Coordinate survey technical reports and user guides to facilitate understanding and effective use of survey data

	Description
	The technical reports for the individual surveys include information on sampling, response rates and weighting. As these activities have been completed by OCSP they will be responsible for the technical write-up. 

	Output
	Required sections for individual survey technical reports

	Lead
	Office for the Chief Statistician and Performance

	Other groups involved
	Survey Managers
Survey Contractors

	Time needed
	9 months (not continuous)

	Planned start date
	Spring 2013

	Planned completion date
	End of 2013


� http://www.scotland.gov.uk/Topics/Statistics/About/SurveyStrategy


� http://www.scotland.gov.uk/Topics/Statistics/scotstat/SPSCC





PAGE  
8

