## Sheet1
Description of Known Issue | Location | Date Identified | Current Status (Open, Closed, In Progress) | Disposition (Planned, Deferred, In Progress) | Remediation Timeline | Available Workarounds | Additional Comments
Criterion 2.4.7 (WCAG 2.1) Focus Visible: Any keyboard operable user interface has a mode of operation where the keyboard focus indicator is visible. (Level AA) When navigating the site using the keyboard there is no visual indicator to show the user which anchor or link is currently selected. | Sitewide | 2019-10-01 | In Progress | In Progress | This work is currently underway and will continue until completed. Anticipated completion is September 2020 at the latest. | The browser will show the target of the link in the bottom left of the screen and we have ensured our URLs are meaningful to allow users using keyboard navigation to sucessfully navigate the site.
Criterion 1.4.3 (WCAG 2.1) Contrast (minimum) The visual presentation of text and images of text has a contrast ratio of at least 4.5:1 (Level AA) There is low contrast text throughout the site. | Sitewide | 2019-10-01 | In Progress | In Progress | This work is currently underway and will continue until completed. Anticipated completion is September 2020 at the latest. | All of our text is selectable, identifiable by screenreaders, and compatible with assistive technologies which can alter contrast. We also provide the text-to-speech software "browsealoud" on the site.
Criterion 1.3.1 (WCAG 2.1) Info and Relationships: Information, structure, and relationships conveyed through presentation can be programmatically determined or are available in text. (Level A) Some structural elements are not appropriately labelled to provide screenreader users with clarity over the structure of the page. | Sitewide | 2019-10-01 | In Progress | In Progress | This work is currently underway and will continue until completed. Anticipated completion is September 2020 at the latest.
Criterion 3.3.2 (WCAG 2.1) 3.3.2 Labels or Instructions: Labels or instructions are provided when content requires user input. (Level A) Some forms do not have appropriate labelling. This means that a screenreader user would have no way of knowing what data the form requires. | Sitewide | 2019-10-01 | In Progress | In Progress | This work is currently underway and will continue until completed. Anticipated completion is September 2020 at the latest. | There is redundant text labelling adjacent to the entry boxes.
Criterion 1.1.1 (WCAG 2.1) 1.1.1 Non-text Content: All non-text content that is presented to the user has a text alternative that serves the equivalent purpose, except for the situations listed below. (Level A) Some images do not have a text alternative, so people using a screen reader cannot access the information. | Microsites/subdomains www.eqhria.scottishhumanrights.com & www.careaboutrights.scottishhumanrights.com | 2019-10-01 | Open | Planned |  | These sites are archives, we are working on migrating the information contained on these sites over to the main website platform.
Criterion 2.4.7 (WCAG 2.1) Focus Visible: Any keyboard operable user interface has a mode of operation where the keyboard focus indicator is visible. (Level AA) When navigating the site using the keyboard there is no visual indicator to show the user which anchor or link is currently selected. | Microsites/subdomains www.eqhria.scottishhumanrights.com & www.careaboutrights.scottishhumanrights.com | 2019-10-01 | Open | Planned |  | These sites are archives, we are working on migrating the information contained on these sites over to the main website platform.
Criterion 2.4.1 (WCAG 2.1) 2.4.1 Bypass Blocks: A mechanism is available to bypass blocks of content that are repeated on multiple Web pages. (Level A) There is no option to skip navigation or skip repeated content. | Microsites/subdomains www.eqhria.scottishhumanrights.com & www.careaboutrights.scottishhumanrights.com | 2019-10-01 | Open | Planned |  | These sites are archives, we are working on migrating the information contained on these sites over to the main website platform.